## Slide 1
NCEP Production Suite Review
Program Manager, Integrated Dissemination Program: Luis Cano
NWS Integrated Dissemination Program
December 4, 2013

## Slide 2: Agenda
Integrated Dissemination Program (IDP)
  Overview
  Capability Improvement Timelines
  Questions

## Slide 3: IDP Overview
IDP plans to deliver NOAA Wide Dissemination Services in a phased approach
In Phase 1, IDP’s focus is on executing against its 3 Program, Project and Activities (PPAs) requirements: NWS Ground Readiness Project, NWS Telecommunication Gateway (Re-architecture), and NWS Next Generation IT Web Services.

## Slide 4: IDP Phase 1 Challenges/Benefits
Aging Infrastructure
Backup Telecommunication Gateway with 74% operational capability
Disbursed dissemination applications
Multiple source of weather data
Inadequate Networks
Next generation of satellite (volume increase) about to launch
Super Computer Upgrade (volume increase)
Current State (Challenges)
Integrated Dissemination Program
Phase 1 Initiatives
Target State (Benefits)
Redundant Dissemination Infrastructure at diverse locations with 100% primary and backup operational capability
NWSTG Re-architected functionality
Disseminate a single source of weather data to NWSTG consumers, aviation decision makers, and others
Fully exploit and benefit from new observations and products
Improved and upgraded NWS Networks with increased bandwidth
IDP
Dissemination Infrastructure
NWSTG Re-architecture Functionality
NextGen IT
Direct Readout (GRB Antennas)
SBN Upgrade &
Network Upgrade & Optimization

## Slide 5
Primary Site (NCWCP)
FY13
FY17
FY16
FY15
FY14
O&M
Design & Build out
Phase 2
Design & Build out
Phase 1
Eng’g Study, Req’ts & Acq’n
Design & Build Out
Backup Site
(DSRC)
Phase 2–NCWCP Build out complete
O&M
Req’ts
Refresh
Re-architecture
Site B-74% Operational Capability
Retire Legacy NWSTG
O&M
Site A - 100% / Site B - 74%
Site A - 100% / Site B - Build and Test
Requirement Phase
Design / Build / Test
Cutover
Backup Site Build out complete
IDP Infrastructure
NWSTG Re-arch Funct.
Re-arch Contract Award
NWSTG Functions at IDP Primary Site
NWSTG Functions at IDP Backup
Web Services Prototype
O&M
Provide NWS Products for FAA Operations
NextGen IT Contract Award
Prototype Dev & Impl
Dev & Impl of NextGen IT Web Services
Acq’n for NextGen IT Web Services
Web Services Prototype Delivered
IDP Web Services Implemented
Augments & reuses same infrastructure
Experimental Operations
NextGen IT
GVAR
Antennas
GRB
Antennas
& SBN Upgrade
O&M
GRB Antennas Installed
GRB Antenna
Contract Award
O&M
Dev & Impl
GRB Assessment & Site Survey (Req’ts & Acq’n)
Retiring GVAR Antennas
GOES-R Launch
Direct Readout (GRB)
GRP Network Upgrade & Opt.
Current
Networks
GRP Network Upgrade & Optimization
O&M
Upgrade & Optimization Contract Award
O&M
Build & Transition to GRP Network
Req’ts & Acq’n
Network Upgraded & Optimized
Retire Legacy
NWS Networks
Phase 1 - Current NCWCP Compute Farm Augmented
NextGen IT Web Services
  IDP Phase 1 Timeline
  High Level View
SBN Upgraded
to Full Transponder

## Slide 6: IDP Phase 1 Timeline IDP Dissemination Infrastructure Sites
IDP Primary Site
at NCWCP
(College Park, MD)
FY13
FY17
FY16
FY15
FY14
IDP Primary Site (Phase 1)
Current Compute Farm
Augmented at NCWCP
Build out IDP
Backup Site (Phase 3) at
DSRC (Boulder, CO)
O&M
Cutover
O&M
Build out
IDP Primary Site
Phase 2
Build out
IDP Primary Site
Phase 1
Facilities Study,
Planning &
Initiate Construction
IDP Backup Site
at DSRC
(Boulder, CO)
Build out IDP
Primary Site (Phase 2) at
NCWCP (College Park, MD)
O&M
Capability Improvements Provided by IDP Dissemination Infrastructure:
Redundant primary and backup capability in two diverse locations (College Park, MD and
Boulder, CO)
Scalable architecture
Hot Backup
Centralized and consolidated infrastructure
Ability to disseminate large amount of data
Secured sites at (near) Trusted Internet Connections Access Providers (TICAP) locations
Requirement and Acquisition Phase
Design, Build, and Test Phase
Cutover
Operations and Maintenance
Retire/Phase Out
Build out
IDP Primary Site
Phase 3

## Slide 7: IDP Phase 1 Timeline NWSTG Re-Architecture Functionality
NWSTG Refresh
NWSTG
Re-architecture
FY13
FY17
FY16
FY15
FY14
NWSTG Site B -74% Operational Capability
NWSTG Functions
on IDP Backup
Dissemination Service
NWSTG Primary – 100%
Operational Capability
NWSTG Backup -100%
Operational Capability
Retire Legacy NWSTG
NWSTG Functions
on IDP Primary
Dissemination Services
O&M
Requirement
Phase
Cutover
NWSTG Refresh
Site A = SSMC2 Silver Spring, MD
Site B = NESCC Fairmont, WV
NWSTG Re-architecture
IDP Primary = NCWCP College Park, MD
IDP Backup = DSRC Boulder, CO
Retire Legacy
NWSTG
O&M
Site A – 100%
Site B -Build and Test
Requirement Phase
Design & Build &Test of NWSTG Function
Cutover
Capability Improvements Provided by NWSTG Re-architecture:
Redundant primary and backup capability in two diverse locations (College Park, MD and Boulder, CO) with 100% hot-hot operational capability on primary (NCWCP College Park, MD) and backup (DSRC Boulder, CO) sites.
Ability to process anticipated increases in environmental data volume from new satellites (e.g. GOES-R and JPSS), increases and enhancements to environmental model prediction (e.g. HRRR), and radar data.
Requirement and Acquisition Phase
Design, Build, and Test Phase
Cutover
Operations and Maintenance
Retire/Phase Out
Site A – 100%
Site B – 74%
Site A – 100%
Site B – 80%
Site A – 100%
Site B – 90%
IDP A – 100%
IDP B – 100%

## Slide 8: IDP Phase 1 Timeline NextGen IT
NextGen
Prototype
NextGen IT
FY13
FY17
FY16
FY15
FY14
O&M
NOAA IDP
Web Services Provides NWS Products to FAA SEP 2016
NextGen IT Contract Award
Web Services Prototype Dev & Impl
Dev & Impl of NextGen IT Web Services
Acq’n for NextGen IT Web Services
NOAA IDP NextGen Web Services Prototype Delivered Sept 2013
(~400 Products)
NOAA IDP Web Services Implemented
Dec 2015
(~1300 Products)
Capability Improvements Provided by NextGen IT Web Services:
Common logical entry point for data discovery and access
Consolidation and standardization of data formats
Standardized OGC-compliant Web Services access
Standards-based registry/repository
Near term replaces legacy FAA Bulk Weather Telecommunications Gateway (FBWTG) connection from NWS to FAA
Mid term support for NWS AWIPS consumers
Long term support for other users (NOAA, DoD, DHS, public)
Augments & reuses same infrastructure
Experimental Operations
Requirement and Acquisition Phase
Design, Build, and Test Phase
Cutover
Operations and Maintenance
Retire/Phase Out

## Slide 9: IDP Phase 1 Timeline Direct Readout (GRB Antennas)
GVAR Antennas
Direct Readout
(GRB Antennas)
& SBN Upgrade
FY13
FY17
FY16
FY15
FY14
O&M
GRB Antennas
Installed
Direct Readout (GRB Antenna) Contract Award
Operations and Maintenance
Development & Implementation
GRB Assessment and Site Survey
(Requirement & Acquisition Phase)
Retiring GVAR
Antennas
Capability Improvements Provided by Direct Readout:
Ensure NCEP Remote Centers and Alaska and Pacific Regions can fully exploit GOES-R observations by GOES-R launch (currently scheduled for October 2015).
GOES-R Launch
Requirement and Acquisition Phase
Design, Build, and Test Phase
Cutover
Operations and Maintenance
Retire/Phase Out
SBN Upgraded to
a Full Transponder

## Slide 10: IDP Phase 1 Timeline NWS GRP Network (CONUS and OCONUS) Upgrade & Optimization
NWS Current
Networks
NWS GRP
Network Upgrade
& Optimization
FY13
FY17
FY16
FY15
FY14
O&M
NWS GRP Network Upgrade & Optimization Contract Award
O&M
Build & Transition to GRP Network
Requirement &
Acquisition Phase
NWS GRP Network
Upgraded and Optimized
Capability Improvements Provided by NWS GRP Network Upgrade & Optimization:
Improve and consolidate NWS networks
Provide increased bandwidth
Upgrade information technology infrastructure and networks at Weather Forecast Offices (WFO), River Forecast Centers (RFC), National Centers for Environmental Prediction (NCEP), and Advanced Weather Interactive Processing System (AWIPS) Network Control Facilities.
Requirement and Acquisition Phase
Design, Build, and Test Phase
Cutover
Operations and Maintenance
Retire/Phase Out
Retire Legacy
NWS Networks